## Cover
Risk Register
Group C: Champions Consultancy
Kalyani, Monika, Disha, Shruti
2021-10-04

## Risk Register (hidden)
Risk Register
Project Name |  |  | Elite
Project Lead |  |  | PL Name
Sponsor |  |  | Sponsor Name
Purpose: To document the description and assessment of risks and to offer action plans to respond to risks. The Risk Register provides a reference for the project team and supports their need to be apprised of and evaluate the risks.
A risk is an uncertain event or condition, which if it occurs, has a positive or negative affect on a project’s objectives.
All risks will be listed on the Risk Register, and only those risks with a risk level of Medium or above with be listed on the Detailed Risk Response Form.
Use caution not to list all business risks, just list the risks that relate to the current project.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab , refer to bottom of page.>
Date Identified | Risk No. | Deliverable | Risk Description | Category | Potential Impact Description | Risk Owner | Likelihood of Occurrence | Impact | Likelihood Risk Value | Impact Risk Value | Risk | Response | Response Comments | Status | Loss Hours/Cost | Preventative Risk Hours/Cost | Response | Preventive Strategic Plan | Contingency Strategic Plan | Date of Response Implemented
Accountable
2018-04-21 | 1 | web coding | Resource's disability leave may be longer than planned. | Schedule Risk | delay to web coding | Jerry | High | Medium | 3 | 2 | 5 | Mitigate | change order of tasks | New | 4w/$8000 | 0 | Mitigate | contact contract agencies ahead of time to get resumes | hire a contractor, resulting in $5000 and 2 week delay.
2013-03-21 | 2 | training | Users may need additional training class | Training Risk | could delay deployment, incr cost | Lisa | Medium | High | 2 | 3 | 5 | Avoid | book additional classes | New | 4w/$40,000 | 1w/$10,000 | Avoid | Work with students to help ensure material understood | schedule additional training week
2013-03-19 | 3 | infrastructure | Shortage of processors may delay production and shipment of servers | Schedule Risk | delay to setup of environments | Stephen | Low | Medium | 1 | 2 | 3 | Mitigate | change order of tasks | New | 2w/$10000 | 0 | Mitigate | order servers sooner | pay for rush shipping $1000
| 4 | [5 empty] | Medium | Low | 2 | 1 | 3
| 5 | [5 empty] | Low | Low | 1 | 1 | 2
| 6 | [5 empty] | Low | Low | 1 | 1 | 2
| 7 | [5 empty] | Low | Low | 1 | 1 | 2
| 8 | [5 empty] | Low | Low | 1 | 1 | 2
| 9 | [5 empty] | Low | Low | 1 | 1 | 2
| 10 | [5 empty] | Low | Low | 1 | 1 | 2
| 11 | [5 empty] | Low | Low | 1 | 1 | 2
| 12 | [5 empty] | Low | Low | 1 | 1 | 2
| 13 | [5 empty] | Low | Low | 1 | 1 | 2
| 14 | [5 empty] | Low | Low | 1 | 1 | 2
| 15 | [5 empty] | Low | Low | 1 | 1 | 2
| 16 | [5 empty] | Low | Low | 1 | 1 | 2
| 17 | [5 empty] | Low | Low | 1 | 1 | 2
| 18 | [5 empty] | Low | Low | 1 | 1 | 2
| 19 | [5 empty] | Low | Low | 1 | 1 | 2
| 20 | [5 empty] | Low | Low | 1 | 1 | 2
| 21 | [5 empty] | Low | Low | 1 | 1 | 2
| 22 | [5 empty] | Low | Low | 1 | 1 | 2
| 23 | [5 empty] | Low | Low | 1 | 1 | 2
| 24 | [5 empty] | Low | Low | 1 | 1 | 2
| 25 | [5 empty] | Low | Low | 1 | 1 | 2
| 26 | [5 empty] | Low | Low | 1 | 1 | 2
| 27 | [5 empty] | Low | Low | 1 | 1 | 2
| 28 | [5 empty] | Low | Low | 1 | 1 | 2
29
30
31
32
33
34
35

## Risk Analysis
Risk Analysis Matrix
Rating are subjective, so we recommend the following general guidelines.
Likelihood and Impact
| Impact | High | 4 points | 5 points | 6 points | Likelihood that the event will occur: Low [ 0 - 50% likelihood of occurrance ] Medium [ 51% to 75% likelihood of occurrance ] High [ > 76% likelihood of occurrance ]
|  | Medium | 3 points | 4 points | 5 points | Impact if the event occurs: Low [ Less than 10% of the project budget ] Medium [ Between 10% - 25% of the project budget ] High [ More than 25% of the project budget ]
|  | Low | 2 points | 3 points | 4 points
|  |  | Low | Medium | High
Likelihood

## Register Instructions
Risk Register Instructions
Field | Description
Date Identified | Use the format mm/dd/yy to list the date the risk was first identified.
Risk No. | List the Risk Number in sequential order, 1, 2 etc.
Deliverable | List the deliverables associated with the risk. Tie back to the requirements number, test case number, request for change number or WBS number. If a deliverable cannot be tied, leave this blank
Risk Description | Describe the risk - an event or condition - which if it occurs, could have a positive or negative affect on a project's objectives. For example, the technology that is being purchased will not be supported by the manufacturer in 2 months.
Category | Risk Categories are sources of potential risk for classification. Select the appropriate risk category from the drop list. Values include Schedule Risk, Budget Risk, Scope Risk, Requirements Risk, Milestone Risk, Deployment Risk, Training Risk, Change Leadership Risk, Business Organizational Impact Risk, Resource Risk, Customer Risk, Technical Risk, External Risk, and Vendor Risk.
Potential Impact Description | State how the risk would affect the project if it occurs, (i.e.: not having manufacturer support for this technology would be have an adverse affect to the roll out).
Risk Owner | List the name of the person that has ownership of this risk, and the accountability to make certain the response plan is implemented.
Likelihood of Occurrence | Indicate the likelihood that the risk will occur using the scale - Low, Medium, or High. Low - 0-50% chance of occurrence, Medium - 51-75% chance of occurrence, High - >76%.
Impact | State how the risk could affect the project if it occurs using the scale - Low, Medium, or High. Low - less than 10% of the project budget, Medium - 10 -25% of the project budget, High - more than 25% of the project budget.
Risk Level | Determine the overall risk assessment by summing the likelihood of occurrence and the impact. The risk assessment will be automatically calculated when using the spreadsheet. The minimum threshold for completing the Risk Response Form is 5. If the overall risk assessment is 5 or greater, complete the Detailed Risk Response Form.
Response | Choose from one of the responses below. Accept: Accept the consequences - do nothing. Will not hamper the overall success of the project, but may delay a milestone. Avoid: Eliminate the cause of the risk - change the project direction to protect the project objectives from this impact. Mitigate: Take action to reduce the likelihood that the risk will occur to an acceptable threshold. Transfer: Transfer the responsibility for managing the risk, including ownership, and acceptance of consequences. Transfer does not eliminate the risk.
Response Comments | Provide details describing the selected response.
Status | Select from the list to identify the status of the risk - New, Assigned, Closed, Cancelled, On-Hold, Project Team Review, Steering Committee Review, SLT Review, Mitigate Action Approved to Proceed, Mitigation Action in Progress, Mitigation Action Complete
Loss Hour/ Cost | Determine the anticipated number of labor hours or cost that will be lost if the risk occurs.
Preventative Risk Hours/Cost | Establish the anticipated number of hours or cost that it will take to determine and create a preventative strategy or contingency plan.
Response | Choose from one of the responses below. Acceptance: Accept the consequences, will not hurt the overall project success, but may delay a milestone. Avoidance: Eliminate the cause of the risk - change the project direction to protect the project objectives from this impact. Mitigation: Take action to reduce probability that the risk will occur to an acceptable threshold. Transference: Transfer the responsibility of managing the risk, including ownership, and acceptance of consequences. Transference does not eliminate the risk.
Preventive Strategic Plan | Determine what steps will be taken to prevent this risk from occurring. Example: Traveling to a site with a mobile lab, including 14 laptops, 250 feet of cable, 2 hubs and 1 server. The Ethernet cards in the laptops could possibly be damaged in the shipping process. To try to prevent this from occurring, special packaging will be used to ship the mobile lab.
Contingency Strategic Plan | List the backup plan that will be implemented if the risk event actually occurs. Example: The person traveling will carry two additional Ethernet cards with them. In each city, a vendor has been researched and contacted prior to deployment in that city to make sure laptop inventory is available if needed.

## Validation Lists
Category | Likelihood of Occurrence | Impact | Response | Status
Schedule Risk | High | High | Accept | New
Budget Risk | Medium | Medium | Avoid | Assigned
Scope Risk | Low | Low | Mitigate | Closed
Requirements Risk |  |  | Transfer | Cancelled
Milestone Risk |  |  |  | On-Hold
Deployment Risk |  |  |  | Project Team Review
Training Risk |  |  |  | Steering Committee Review
Change Leadership Risk |  |  |  | Management Review
Organizational Impact Risk |  |  |  | Mitigate Action Approved to Proceed
Resource Risk |  |  |  | Mitigate Action in Progress
Customer Risk |  |  |  | Mitigate Action Complete
Technical Risk
External Risk
Vendor Risk

## Risk Leading Questions
Leading Questions for Risk Identification
Purpose: Use the following as examples of project risks to assist in identification of risks. This is not an all-inclusive list, but rather to serve as memory joggers for Project Management Processes and a Software Development Lifecycle. The current proje
Project Management | Software Development
Opportunity Assessment | Opportunity Assessment
Are the project objectives vague or unclear? | Does this project involve changing major business processes or is business personnel having to perform new tasks?
Does the business partner have enough time to focus on this project?
Concept Phase
Initiating Process | Are there a large number of interfacing systems or interfacing departments?
Are the deliverables clearly understand by all?
Are the critical success factors clear and measurable? | Requirements
Is the business sponsor / business team committed to the success of the project? Are the expectations of their involvement clearly laid out? | Are the requirements constantly changing or unclear?
Has the business sponsor changed during the project? | Has enough time been spent on requirements development?
Does the business and/or IT senior leadership believe in the business case for the project?
Development
Planning | Are technologies being introduced in the organization's environment that have not been tested?
Is the schedule realistic or are activities and tasks overly optimistic?
Is the budget realistic or based on unrealistic estimates? | Testing
Does the project involve a large number of users? | Has performance testing been included in the test planning?
Is the project heavily reliant on third party resources to complete key deliverables on time? Does the team have prior experience with this company? | Have adequate resources (time, money, resources) been allocated to do comprehensive testing end to end?
Is there a high level of turnover in the business or IT area affected? Is there a contingency plan?
Are team members' roles clearly laid out and documented? | Documentation and Training
Is there a clear assignment of tasks and ownership among team members? | Has sufficient training been planned in the schedule?
Is there any slack time or contingency built into the plan?
Is there adequate Change Enablement / Communication plan in place? | Deployment
Does the project manager have enough time to focus on this project? | Are there major business functions that could be interrupted if the project is not implemented successfully?
Executing/Controlling | Post Deployment
Are there multiple third party companies involved in the project? | Has the ownership of outstanding items been passed to the appropriate business area?
Does the current IT team have prior experience with this type of project?
Are there geographical constraints that will inhibit the success of the project?
Is risk being managed?
Is the budget being managed?
Is the schedule being managed?
Have key project resources turned over or changed during the course of the project?
Closing
Has all deliverables been met?
Are the customers satisfied with the product / service?

## RiskRegister_CC
Risk Register
Project Name |  |  | Elite Art Cloud Solution
Project Lead |  |  | Project Manager from Champion Consultancy
Sponsor |  |  | Owner: Jake Towers
Purpose: To document the description and assessment of risks and to offer action plans to respond to risks. The Risk Register provides a reference for the project team and supports their need to be apprised of and evaluate the risks.
A risk is an uncertain event or condition, which if it occurs, has a positive or negative affect on a project’s objectives.
All risks will be listed on the Risk Register, and only those risks with a risk level of Medium or above with be listed on the Detailed Risk Response Form.
Use caution not to list all business risks, just list the risks that relate to the current project.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab , refer to bottom of page.>
Date Identified | Risk No. | Deliverable | Risk Description | Category | Potential Impact Description | Risk Owner | Likelihood of Occurrence | Impact | Likelihood Risk Value | Impact Risk Value | Risk | Response | Response Comments | Status | Loss Hours/Cost | Preventative Risk Hours/Cost | Response | Preventive Strategic Plan | Contingency Strategic Plan | Date of Response Implemented
2021-10-04 | 1 | Training | Training from Solution Vendor to Elite Art Employees post project implementation | Training Risk | Improper usage of the system and lack of system understanding | Solution Vendor and Business Manager | Medium | High | 2 | 3 | 5 | Mitigate | Follow up with the solution vendor and the employees about the cloud solution training | New | 3d/$1500 | 0 | Mitigate | Communicate the schedule in advance to avoid this risk | Project Schedule to be moved ahead until the employees are trained | N/A
2021-10-04 | 2 | Solution | Delay from solution vendor | Schedule Risk | Delay in getting and launching the prepackaged cloud solution | Business Manager | Low | High | 1 | 3 | 4 | Mitigate | Follow up with the Solution Vendor to track the update of the cloud solution | New | 1w/$4000 | 0 | Mitigate | Communicate the hard deadline with the solution vendor | Move the project schedule until the solution availability | N/A
2021-10-04 | 3 | Project Continuation | Insufficient Funding | Budget Risk | Project Sponsor (Jake might not have sufficient fund) | Business Manager & Store Owner | Medium | Medium | 2 | 2 | 4 | Accept | Contact project sponsor and follow up with all the concern stakeholders | New | 1w/$5750 | 0 | Mitigate | Communicate the project cost with Project Sponsor and have sufficient contingency reserve | Cloud solution can still be implemented with less fuctionality | N/A
2021-10-04 | 4 | Requirement Gathering | Misunderstanding of requirements/terms | Requirements Risk | Incorrect comprehension of requirement by Solution Vendor and Champion Consultancy | Champion Consultancy and Solution Vendor | Low | Medium | 1 | 2 | 3 | Mitigate | Follow up with Champion Consultancy and Solution Vendor to rectify the misunderstandings | New | 1w/$4400 | 1w/1400 | Mitigate | Constant follow up and approval from key stakeholders | Rectify the system requirements with all key stakeholder, this may push the project triple constraint. | N/A
2021-10-04 | 5 | Solution Completion/Timeline | Change of requirement | Requirements Risk | Project Sponsor requesting customization of the solution post project requirement approval | Champion Consulting and Solution Vendor | Low | Medium | 1 | 2 | 3 | Accept | Accept the end user's request and deliver in current on future sprint but add it to the roadmap | New | 1w/$2000 | 1w/$1200 | Accept | Clearly communicate the current requirements and potential future system requirements to match it with the project scope | A contigency plan in case of a delay needs to be in place with a budget to add in resourse through various phases of the project. | N/A
2021-10-04 | 6 | Project Scope | Project Scope | Scope Risk | Scope creep | Project Manager | Medium | High | 2 | 3 | 5 | Mitigate | Avoid scope creep and perform all the actions in the limit of the project scope | New | 3d/$5280 | 0 | Mitigate | Clarifying the requirements and getting written approval for them can help in reducing the chance of scope creep | Communicate the project scope with the key stakeholders and communicate that project budget and timeline will change if the scope is widened. | N/A
2021-10-04 | 7 | Connect to 3rd party applications | Interfacing Issue | Technical Risk | API/Interface | Solution Vendor and 3rd Party Vendor | Medium | High | 2 | 3 | 5 | Transfer | Contact solution Vendor and 3rd Party Vendor and follow up | New | 1d/$2460 | 1d/$1000 | Accept | Keep the stakeholders in loop with all the communication taking place between Solution Vendor and 3rd Party Vendor | Project schedule and budget may get affected by this risk | N/A
2021-10-04 | 8 | Secured solution | Cloud Security | Technical Risk | Mishandling of sensitive data causing security threat and challenges | Solution Vendor | Medium | High | 2 | 3 | 5 | Mitigate | Identify the security breach and communicate with solution vendor and stakeholders | New | 1d/$2000 | 1d/$100 | Accept | Have latest enhanced security for cloud services from Solution Vendor | To restore the cloud system and add additional security in place which will increase the budget of the project | N/A
2021-10-04 | 9 | Successful data migration | Data migration post solution implementation | Technical Risk | Incorrect migration of data causing data loss | Business Manager and Solution Vendor | Medium | High | 2 | 3 | 5 | Mitigate | To identify and review the missing or bad data. | New | 1w/$5000 | 1w/$1500 | Mitigate | Have a robust solution and clean the data before loading them into the cloud solution | Require additional budget to request Solution Vendor to perform data cleaning and consistency in the Elite Art Data on the cloud | N/A
2021-10-04 | 10 | Continuous network connection | Intermittent Network Connectivity | Technical Risk | Unavailability of cloud solution or internet connection | Solution Vendor and 3rd Party Internet Provider | Low | Low | 1 | 1 | 2 | Transfer | Identify and communicate the downtime with solution users |  | 1d/$1400 | 0 |  | Continuous update about network availability | Follow up with network service provider team | NA
2021-10-04 | 11 | Quality Assurance | End- User Acceptance | Requirements Risk | Project Sponsor (Jake might not be satisfied with some solutions) | Business Manager & Store Owner | Low | Low | 1 | 1 | 4 | Accept | Follow up with Project Sponsor and business manager to confirm the outcomes and goals from the cloud solution implementation |  | 1w/$2400 | 1w/$3000 |  | Communicate and confirm goals/outcomes with all key stakeholders | Confirm the functionalities that need modification and push the project schedule to include the new scope, budget and timeline | NA
2021-10-04 | 12 | Seamless functioning of cloud solution | Unavailability of hardware/software resource | Resource Risk | Resources are not bought or available when required | Business Manager & Store Owner | Low | Low | 1 | 1 | 2 | Avoid | Track and communicate the availability of hardwares and softwares |  | 1d/$2000 | 0 |  | Agree upon and define a definitive delivery day for the hardware | Project plan might be shifted by a couple of days due to delay in the hardware availability | NA
2021-10-04 |  | Availability of all key stakeholders | Key stakeholder resigns | Resource Risk | Major obstacles in on-time project delivery | Business Manager, Solution Vendor and Champion Consultancy |  |  |  |  | 2 | Accept | Track the availability of all key stakeholders |  | 1d/$1000 | 0 |  | Document every project detail and arrange for replacement of a trained employee once unavailability is confirmed | Use project documentation and train the newly hired employee to continue the project implementation | NA

## Risks Identified by CC
Date: October-04-2021 | Risk | Reason | Risk Owner | Category | Overlapping with
1 | Delay in training | Delay in training the store employees after project implementation | Solution Vendor | Training Risk
2 | Delay from solution vendor | Delay in getting and launching the prepackaged cloud solution | Business Manager | Schedule Risk | Delay in Training
3 | Insufficient Funding | Project Sponsor (Jake might not have sufficient fund) | Business Manager & Store Owner | Budget Risk
4 | Misunderstanding of requirements/terms | Incorrect comprehension of requirement by Solution Vendor and Champion Consultancy | Champion Consultancy and Solution Vendor | Requirement Risk
5 | Change of requirement | Project Sponsor requesting customization of the solution post project requirement approval | Champion Consulting and Solution Vendor | Requirement Risk
6 | Project Scope | Scope creep | Project Manager | Scope Risk
7 | Interfacing Issue | API/Interface | Solution Vendor and 3rd Party Vendor | Technical Risk
8 | Cloud Security | Mishandling of sensitive data causing security threat and challenges | Solution Vendor | Technical Risk
9 | Data migration post solution implementation | Incorrect migration of data causing data loss | Business Manager and Solution Vendor | Technical Risk
10 | Intermittent Network Connectivity | Unavailability of cloud solution or internet connection | Solution Vendor and 3rd Party Internet Provider | Technical Risk
11 | End- User Acceptance | Project Sponsor (Jake might not be satisfied with some solutions) | Business Manager & Store Owner | Requirement Risk
12 | Unavailability of hardware/software resource | Resources are not bought or available when required | Business Manager & Store Owner | Resource Risk
13 | Key stakeholder resigns | Unavailability of cloud solution or internet connection | Business Manager, Solution Vendor and Champion Consultancy | Resource Risk